## Summary (hidden)
Project | Edoc Mobile
Technical | React Native
Efforts(mds) | 185
Start | 0
Finish | 0
|  | No. | Task | Finish
|  | 1 | Thiết kế cấu trúc site | 2017-07-05
|  | 2 | Quản trị | 2017-06-29
|  | 3 | Danh mục dùng chung | 2017-06-16
|  | 4 | Dự kiến chương trình công tác năm | 2017-06-23
|  | 5 | Dự án luật | 2017-06-23
|  | 6 | Pháp lệnh | 2017-06-30
|  | 7 | Các vấn đề quan trọng Quốc gia | 2017-06-30
|  | 8 | Hoạt động giám sát tối cao của Quốc hội | 2017-07-07
|  | 9 | Xây dựng dự kiến nội dung kỳ họp | 2017-07-07
|  | 10 | Xây dựng dự kiến chương trình họp chi tiết | 2017-07-14
|  | 11 | Xây dựng chương trình ngày làm việc của Quốc hội | 2017-07-14
|  | 12 | Quản lý phân công lãnh đạo quốc hội | 2017-07-11
|  | 13 | Biểu mẫu | 2017-07-19
|  | 14 | Báo cáo | 2017-07-19
|  | 15 | Tài liệu | 2017-07-24
Grand Total

## Plan
Lv1. | Lv2. | No. | Task | Detail | Efforts(mds) | Start | Finish | Resource | %Complete | Comment
1 | 0 | 1 | Architect |  |  |  | 0
1 | 1 | 1.1 |  | Layout |  |  |  | LNTNHAN | 100%
1 | 2 | 1.2 |  | Definition Language |  |  |  | LNTNHAN | 100%
1 | 3 | 1.3 |  | Login |  |  |  | LNTNHAN | 100%
1 | 4 | 1.4 |  | Logout |  |  |  | LNTNHAN | 100%
1 | 5 | 1.5 |  | Paging
2 | 0 | 2 | Dashboard |  |  |  | 0
2 | 1 | 2.1 |  | Genarate Data |  |  |  | LNTNHAN | 80%
3 | 0 | 3 | Post |  |  |  | 0
3 | 1 | 3.1 |  | Display List + Paging |  |  |  | DDMINH | 100%
3 | 2 | 3.2 |  | Display Detail |  |  |  | DDMINH | 100%
3 | 3 | 3.3 |  | CRUD Post |  |  |  | DDMINH | 100%
3 | 4 | 3.4 |  | Filter |  |  |  | DDMINH | 50%
4 | 0 | 4 | My Learning |  |  |  | 0
4 | 1 | 4.1 |  | Display List Module |  |  |  | DDMINH | 100%
4 | 2 | 4.2 |  | Detail Module |  |  |  | DDMINH | 100%
4 | 3 | 4.3 |  | Filter |  |  |  | DDMINH | 50%
4 | 4 | 4.4 |  | Display Capsules |  |  |  | DDMINH | 100%
4 | 5 | 4.5 |  | Detail Capsule |  |  |  | DDMINH | 100%
4 | 6 | 4.6 |  | Display Capsule Rate |  |  |  | DDMINH | 0%
4 | 7 | 4.7 |  | Filter Capsule |  |  |  | DDMINH | 0%
5 | 0 | 5 | Knowledge Library |  |  |  | 0
5 | 1 | 5.1 |  | List Knowledge Module |  |  |  | DDMINH | 100%
5 | 2 | 5.2 |  | Filter |  |  |  | DDMINH | 0%
5 | 3 | 5.3 |  | Detail Knowledge |  |  |  | DDMINH | 100%
5 | 4 | 5.4 |  | CRUD Knowledge |  |  |  | DDMINH | 100%
5 | 5 | 5.5 |  | CRUD Knowledge Category |  |  |  | DDMINH | 100%
5 | 6 | 5.6 |  | CRUD Knowledge Document |  |  |  | DDMINH | 0%
6 | 0 | 6 | Forums |  |  |  | 0
6 | 1 | 6.1 |  | List Forum |  |  |  | NXSON | 80%
6 | 2 | 6.2 |  | Detail Forum |  |  |  | NXSON | 80%
6 | 3 | 6.3 |  | CRUD Forum |  |  |  | LNTNHAN | 80%
7 | 0 | 7 | Users |  |  |  | 0
7 | 1 | 7.1 |  | List User |  |  |  | NXSON | 80%
7 | 2 | 7.2 |  | Update User |  |  |  | NXSON | 80%
8 | 0 | 8 | Administrator |  |  |  | 0
8 | 1 | 8.1 |  | List Administrator Accounts |  |  |  | LNTNHAN | 80%
8 | 2 | 8.2 |  | Update Administrator Account |  |  |  | NXSON | 80%
8 | 3 | 8.3 |  | Roles |  |  |  | NXSON | 80%
8 | 4 | 8.4 |  | CRUD Role |  |  |  | NXSON | 80%
8 | 5 | 8.5 |  | Import Account from excel
9 | 0 | 9 | Notification |  |  |  | 0
9 | 1 | 9.1 |  | Notificate template |  |  |  | NXSON | 100%
9 | 2 | 9.2 |  | CRUD Notification template |  |  |  | NXSON | 100%
10 | 0 | 10 | Setting |  |  |  | 0
10 | 1 | 10.1 |  | Update site setting |  |  |  | DDMINH | 100%
10 | 2 | 10.2 |  | Site langugae |  |  |  | DDMINH | 0%
10 | 3 | 10.3 |  | Fixbug |  |  |  | LNTNHAN
Finish | [6 empty] | 0
Formulas:
Finish = SUBTOTAL(104,tblPlan[Finish])

## Holiday (hidden)
No. | Date | Description
1
2

## Resources (hidden)
No. | Account | Fullname | Description
1 | LNTNHAN | Lê Ngọc Thanh Nhân
2 | NXSON | Nguyễn Xuân Sơn
3 | DDMINH | Đỗ Đức Minh