## Summary (hidden)
Project | Edoc Mobile
Technical | React Native
Efforts(mds) | 185
Start | 0
Finish | 0
|  | No. | Task | Finish
|  | 1 | Thiết kế cấu trúc site | 2017-07-05
|  | 2 | Quản trị | 2017-06-29
|  | 3 | Danh mục dùng chung | 2017-06-16
|  | 4 | Dự kiến chương trình công tác năm | 2017-06-23
|  | 5 | Dự án luật | 2017-06-23
|  | 6 | Pháp lệnh | 2017-06-30
|  | 7 | Các vấn đề quan trọng Quốc gia | 2017-06-30
|  | 8 | Hoạt động giám sát tối cao của Quốc hội | 2017-07-07
|  | 9 | Xây dựng dự kiến nội dung kỳ họp | 2017-07-07
|  | 10 | Xây dựng dự kiến chương trình họp chi tiết | 2017-07-14
|  | 11 | Xây dựng chương trình ngày làm việc của Quốc hội | 2017-07-14
|  | 12 | Quản lý phân công lãnh đạo quốc hội | 2017-07-11
|  | 13 | Biểu mẫu | 2017-07-19
|  | 14 | Báo cáo | 2017-07-19
|  | 15 | Tài liệu | 2017-07-24
Grand Total

## Plan
Lv1. | Lv2. | No. | Task | Detail | Efforts(mds) | Start | Finish | Resource | %Complete | Comment
1 | 0 | 1 | Intro |  |  |  | 0
1 | 1 | 1.1 |  | Display intro screen |  |  |  | LNTNHAN | 80%
2 | 0 | 2 | Authenticate |  |  |  | 0
2 | 1 | 2.1 |  | Login |  |  |  | LNTNHAN | 100%
2 | 2 | 2.2 |  | Register |  |  |  | LNTNHAN | 100%
2 | 3 | 2.3 |  | Login by Linkedin |  |  |  | LNTNHAN | 0%
2 | 4 | 2.4 |  | Login by Twitter |  |  |  | LNTNHAN | 0%
3 | 0 | 3 | New feed |  |  |  | 0
3 | 1 | 3.1 |  | Display newfeed |  |  |  | LNTNHAN | 100%
3 | 2 | 3.2 |  | Detaile newfeed |  |  |  | LNTNHAN | 100%
3 | 3 | 3.3 |  | Display users like |  |  |  | LNTNHAN | 100%
3 | 4 | 3.4 |  | Comment |  |  |  | LNTNHAN | 70%
3 | 5 | 3.5 |  | Like |  |  |  | LNTNHAN | 70%
3 | 6 | 3.6 |  | Share |  |  |  | LNTNHAN | 70%
4 | 0 | 4 | Post |  |  |  | 0
4 | 1 | 4.1 |  | Post Text |  |  |  | LNTNHAN | 100%
4 | 2 | 4.2 |  | Post Image |  |  |  | LNTNHAN | 100%
4 | 3 | 4.3 |  | Post video |  |  |  | LNTNHAN | 50%
4 | 4 | 4.4 |  | Post link |  |  |  | LNTNHAN | 50%
5 | 0 | 5 | My Learning |  |  |  | 0
5 | 1 | 5.1 |  | Display List Module |  |  |  | NDTHANG | 100%
5 | 2 | 5.2 |  | Detail Module |  |  |  | NDTHANG | 100%
5 | 3 | 5.3 |  | Enrol module |  |  |  | NDTHANG | 100%
5 | 4 | 5.4 |  | Display Recommendation |  |  |  | NDTHANG | 100%
5 | 5 | 5.5 |  | Display Learning history |  |  |  | NDTHANG | 100%
5 | 6 | 5.6 |  | Favarite |  |  |  | NDTHANG | 100%
5 | 7 | 5.7 |  | Dowload |  |  |  | NDTHANG | 0%
5 | 8 | 5.8 |  | Share |  |  |  | NDTHANG | 0%
6 | 0 | 6 | Knowledge Library |  |  |  | 0
6 | 1 | 6.1 |  | List Knowledge Module |  |  |  | NDTHANG | 100%
6 | 2 | 6.2 |  | Detail Knowledge |  |  |  | NDTHANG | 100%
6 | 3 | 6.3 |  | Download |  |  |  | NDTHANG | 0%
6 | 4 | 6.4 |  | Share |  |  |  | NDTHANG | 0%
6 | 5 | 6.5 |  | Favarite |  |  |  | NDTHANG | 100%
7 | 0 | 7 | My Network |  |  |  | 0
7 | 1 | 7.1 |  | My Post |  |  |  | LNTNHAN | 100%
7 | 2 | 7.2 |  | My Friend |  |  |  | LNTNHAN | 100%
7 | 3 | 7.3 |  | My Forums |  |  |  | LNTNHAN | 100%
7 | 4 | 7.4 |  | My Dashboard |  |  |  | NDTHANG | 50%
8 | 0 | 8 | Pofile |  |  |  | 0
8 | 1 | 8.1 |  | Update profile |  |  |  | NDTHANG | 80%
8 | 2 | 8.2 |  | Update password |  |  |  | NDTHANG | 80%
9 | 0 | 9 | Notification |  |  |  | 0 |  | 100%
9 | 1 | 9.1 |  | List notification |  |  |  | NDTHANG | 0%
9 | 2 | 9.2
Finish | [6 empty] | 0
Formulas:
Finish = SUBTOTAL(104,tblPlan[Finish])

## Holiday (hidden)
No. | Date | Description
1
2

## Resources (hidden)
No. | Account | Fullname | Description
1 | LNTNHAN | Lê Ngọc Thanh Nhân
2 | NDTHANG | Nguyễn Đình Thắng